## Lowes INC
Period: | 12 Months |  | Explanations
OKRs of: | Lowes INC, Mooresville NC |  | Confidence Level:
|  |  | 2022-02-01 | not confident to make it until end of Q
Company's IT Vision | Enhancing Lowes Supply Chain Using Kubernetes Clusters in Azure |  | 3 | generally on track, but with uncertainties
1 year strategy: | Strengthening supply chain resilience for Lowes INC with their third party suppliers and contractors |  | 2022-05-04 | very confident to make it until end of Q
Trend:
|  |  | ⬆️ | compared to last check-in things got better
|  |  | ➡️ | no change compare to last check-in
|  |  | ⬇️ | things got worse compared to last check-in
Progress Score:
|  |  | 0 - 39% | current % of achievement from base line to target number
|  |  | 40%-69% | current % of achievement from base line to target number
|  |  | 70%-100% | current % of achievement from base line to target number
OKR CHECK-IN COMMENTS - to be used as preparation for team meetings or 1:1's (overwrite old comments)
|  | owner | Confidence Level | Trend | Progress Score | Trend | last updated | dependencies / alignment requests to other teams | News for peer collegues and on dependencies | Barriers to remove/ Red flag | must win battles next week
Objective 1 | Establish a secure supply chain platform in Azure
Key Result 1a | Implement DevSecops practices across all supply chain applications | Compliance Officer | 4 | ⬆️ | 70% | ➡️ | 2024-01-03 | Request Devops Team to implement automated security checks in CI/CD pipelines | Devops Team has completed the initial setup for CI/CD itegration | Delays in setting up secrets management with HashiCorp Vault | Complete integration of HashiCorp Vault into Kubernetes Cluster
Key Result 1b | Achieve 90% compliance with Kubernetes security standards | Compliance Officer | 3 | ➡️ | 14% | ⬇️ | 2024-01-02 | Align with Infrastructure team to configure Kubernetes RBAC and pod security policies | Infrastruture Team is testing RBAC policies; no issues reported so far | Potential misconfigurations in Kubernetes networking policies need review | Validate RBAC and pod security policies for production workloads.
Key Result 1c | Ensure secure communication between Azure and OCI using Hashicorp Vault. | Cloud Engineer | 2 | ⬆️ | 10% | ⬇️ | 2023-12-27 | Leverage the Security Team to provide compliance guidance and vulnerability reports | Awaiting vulnerability scan results from Security Team
Objective 2 | Minimize Vulnerabilities Across the Supply Chain
Key Result 2a | Detect and fix 95% of vulnerabilities in Dockerfiles and Kubernetes resources. | Security Analyst | 3 | ➡️ | 40% |  | 2024-01-03 | Request Devops Team to automate SAST & DAST Tools. | Devops Team has configured SAST Tools; DAST setup in progress | High False Positives from automated vulnerability scans slowing resolution | Resolve 80% of identified vulnerabilities in critical images
Key Result 2b | Integrate vulnerability scanning tools(Qualys) into the CI/CD pipeline. | DevOps Engineer | 4 | ⬆️ | 60% |  | 2024-01-02 | Coordinate with Infrastructure Team to ensure regular image scanning for vulnerabilities | Infrastructure Team has identified 5 critical vulnerbailities in Docker Images | Limited resources for patching critical vulnerabilities on time. | Activate real-time alerting for Kubernetes Cluster using Falco
Key Result 2c | Monitor and report vulnerabilities in real-time using Prometheus and Falco | Cloud Security Engineer | 3 | ➡️ | 25% |  | 2024-01-05 | Coordinate with the Security Team to set up real-time monitoring with Prometheus and Falco. | Security Team's monitoring dashboard is operational; alerting setup is pending
OKR backlog for later...

## Devops Team
Period: | 12 Months |  | Explanations
OKRs of: | Devops Team |  | Confidence Level:
|  |  | 2022-02-01 | not confident to make it until end of Q
vision: | Devops Application for Lowes Supply Chain |  | 3 | generally on track, but with uncertainties
1 year strategy: | Strengthen Lowe's cloud application security in compliance with PCI-DSS & CCPA |  | 2022-05-04 | very confident to make it until end of Q
Trend:
|  |  | ⬆️ | compared to last check-in things got better
|  |  | ➡️ | no change compare to last check-in
|  |  | ⬇️ | things got worse compared to last check-in
Progress Score:
|  |  | 0 - 39% | current % of achievement from base line to target deadline
|  |  | 40%-69% | current % of achievement from base line to targeted deadline
|  |  | 70%-100% | current % of achievement from base line to target deadline
OKR CHECK-IN COMMENTS - to be used as preparation for team meetings or 1:1's (overwrite old comments)
|  | owner | Confidence Level | Trend | Progress Score | Trend | last updated | dependencies / alignment requests to other teams | News for peer collegues and on dependencies | Barriers to remove/ Red flag | must win battles next week
Objective 1 | Integrate Security into Devops Practices
Key Result 1a | Automate unit Tests, SAST, AND DAST for supply chain applications | Devops Engineer | 4 | ⬆️ | 70% | ⬆️ | 2024-04-05 | Request from Infrastructure Team: Ensure Kubernetes Cluster Configurations support CI/CD pipelines. | CI/CD pipeline integration with SAST tools completed | Technical challenges in configuring DAST for legacy applications | Successfully configure and test DAST for all applications
Key Result 1b | Shift security left by conducting security assessments in 80% of code builds. | Security Control Assessor | 3 | ➡️ | 40% | ➡️ | 2024-05-05 | Request from Security Team: Provide a list of of critical security benchmarks for SAST & DAST | Awaiting feedback from the Infrastructure on security benchmark validation | Inconsistent build enviornments causing SAST tool errors. | standardize build environments to ensure smooth SAST runs.
Infrastructure team confirms cluster readiness for Devsecops pipeline
Objective 2 | Enhance Kubernetes Security
Key Result 2a | Deploy Kubernetes RBAC and pod security policies for all clusters | Kubernetes Engineer | 3 |  | 50% | ➡️ | 2024-05-20 | Request from Infrastructure Team: Apply RBAC policies to Devops-related Kubernetes namespaces. | Infrastrucure team implemented RBAC for Devops namespaces; testing underway | Delays in implementing pod security policies in the staging environment | Apply and validate pod security policies across all environments
Key Result 2b | Use Prometheus and Grafana for real-time cluster monitoring | Kubernetes Engineer | 4 |  | 60% | ⬆️ | 2024-06-23 | Request from Security Team: Monitor Logs for potential misconfigurations in Kubernetes Clusters. | Security Team has begun monitoring cluster activity and sharing insights | Incosistent roles assignments causing access issues in Kubernetes | Resolve access issues by fine-tuning role assignments in RBAC.
OKR backlog for later...
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Significant progress in automating SAST and unit tests, DAST ongoing
Note on F21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moderate confidence due to initial adoption challenges
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RBAC deployed in staging, production pending
Note on F26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High confidence as tools are deployed

## Infrastructure Team
Period: | 12 Months |  | Explanations
OKRs of: | Infrastructure Team |  | Confidence Level:
|  |  | 2022-02-01 | not confident to make it until end of Q
vision: | Secure Infrastructure for Supply Chain Operations |  | 3 | generally on track, but with uncertainties
1 year strategy: | link to yearly strategic goals document |  | 2022-05-04 | very confident to make it until end of Q
Trend:
|  |  | ⬆️ | compared to last check-in things got better
|  |  | ➡️ | no change compare to last check-in
|  |  | ⬇️ | things got worse compared to last check-in
Progress Score:
|  |  | 0 - 39% | current % of achievement from base line to target number
|  |  | 40%-69% | current % of achievement from base line to target number
|  |  | 70%-100% | current % of achievement from base line to target number
OKR CHECK-IN COMMENTS - to be used as preparation for team meetings or 1:1's (overwrite old comments)
|  | owner | Confidence Level | Trend | Progress Score | Trend | last updated | dependencies / alignment requests to other teams | News for peer collegues and on dependencies | Barriers to remove/ Red flag | must win battles next week
Objective 1 | Secure Infrastructure for supply chain operations
Key Result 1a | Configure HashiCorp Vault for secrets management across Kubernetes pods. | Chief Technical Officer | 4 | ⬆️ | 70% | ➡️ | insert date | Request from Devops Team: Confirm CI/CD pipeline compatibility with infrastructure configurations. | HashiCorp Vault integration completed; secrets injection tested successfully | Networking misconfigurations in Kubernetes causing intermittent connectivity issues. | Resolve all Kubernetes networking issues in production
Key Result 1b | Maintain 99.9% uptime for Kubernetes clusters supporting retail operations. | Infrastructure Engineer | 3 | ➡️ | 14% | ⬇️ | insert date | Request from Security Team: Provide security policies for configuring HashiCorp Vault and Kubernetes RBAC | Awaiting final approval from Team C on Kubernetes RBAC policies | Delays in acquiring updated compliance guidelines from the Security Team | Finalize and apply RBAC policies in all clusters.
|  |  |  | ⬆️ | 0% | ➡️ | insert date |  | Devops Team confirmed CI/CD pipeline readiness for testing infrastructure configurations
Objective 2 | Monitor and Patch Vulnerabilities | Vulnerability Management Analyst
Key Result 2a | Identify and patch 100% of vulnerabilities in container images within 24 hours | Vulnerability Management Analyst |  |  |  |  | insert date | Request from Devops Team: Provide a list of vulnerable dependencies and Dockerfiles detected during security scans. | Devops Team has flagged 10 critical vulnerabilities in Dockerfiles; patching in progess | Delays in receiving updated vulnerability reports for the Security Team | Patch all critical vulnerabilities in Docker images and dependencies
Key Result 2b | Implement Falco for runtime security monitoring | Vulnerability Management Analyst |  |  |  |  | insert date | Request from Security Team: Share prioritized vulnerability reports and compliance benchmarks | Security Team provided compliance benchmarks; aligning patching priorities accordingly | Incompatibility between patched dependencies and current Kubernetes Configurations | Validate patched configurations in the Kubernetes staging environment
[7 empty] | insert date |  | Infrastructure monitoring tools are fully operational, detecting anomalies in real-time.
OKR backlog for later...

## Security Team
Period: | 12 Months |  | Explanations
OKRs of: | Ensure compliance and Monitor Security |  | Confidence Level:
|  |  | 2022-02-01 | not confident to make it until end of Q
vision: | Strenghten PCI-DSS for Lowe's Supply chain Operations |  | 3 | generally on track, but with uncertainties
1 year strategy: | link to yearly strategic goals document |  | 2022-05-04 | very confident to make it until end of Q
Trend:
|  |  | ⬆️ | compared to last check-in things got better
|  |  | ➡️ | no change compare to last check-in
|  |  | ⬇️ | things got worse compared to last check-in
Progress Score:
|  |  | 0 - 39% | current % of achievement from base line to target number
|  |  | 40%-69% | current % of achievement from base line to target number
|  |  | 70%-100% | current % of achievement from base line to target number
OKR CHECK-IN COMMENTS - to be used as preparation for team meetings or 1:1's (overwrite old comments)
|  | owner | Confidence Level | Trend | Progress Score | Trend | last updated | dependencies / alignment requests to other teams | News for peer collegues and on dependencies | Barriers to remove/ Red flag | must win battles next week
Objective 1 | Ensure Compliance with PCI DSS for Supply Chain Data | CISO
Key Result 1a | Conduct quarterly vulnerability scans on Azure and OCI environments, that host credit card data | Vulnerability Analyst | 4 | ⬆️ | 70% | ➡️ | insert date | Request from Devops Team: Provide test results for SAST, DAST, and security scans | Initial compliance audit completed; minor issues found in Kubernetes configurations. | Incomplete logging configurations in Prometheus, affecting security monitoring. | Complete and verify Prometheus logging for real-time monitoring.
Key Result 1b | Document and address compliance gaps in supply chain applications |  | 3 | ➡️ | 14% | ⬇️ | insert date | Request from Infrastruture Team: Share updated infrastructure configurations for compliance verification | Devops Team provided security scan results; reviewing for compliance gaps | Critical vulnerabilities in Docker images need immediate patching | Remediate all critical vulnerabilities in Docker images.
|  |  | 2 | ⬆️ | 0% | ➡️ | insert date |  | Infrastructure Team shares updated cluster configurations for review
Objective 2 | Improve Incident Response & Communication
Key Result 2a | Set up Slack notifications for Jenkins, Prometheus, and Falco alerts. | [5 empty] | insert date | Request from the Devops Team; Set up automated alerts for security events detected during C/ICD pipeline runs | Slack notifications for Falco and Jenkins have been set up; alerts are personal | Delayed response to alerts due to insufficient log data from Kubernetes Cluster | Finalize and deploy incident response procedures with clear escalation paths
Key Result 2b | Respond to 100% of security incidents within SLA. | Technical Business Analyst |  |  |  |  | insert date | Request from the Infrastructure Team; Configure Prometheus and Falco to send detailed security logs for incident analysis | Infrastructure Team is fine-tuning Prometheus monitoring; Falco integration complete | Unclear alert thresholds in Prometheus leading to excessive false positives. | Optimize Prometheus alert thresholds to reduce false positives and improve response time
[7 empty] | insert date |  | Incident response playbook updated and shared with all Teams
OKR backlog for later...